## Sheet1
Date | Discussions | Progress | Testing Done | Bugs Found/Fixed | Tools
Feb. 8th | Discussed the different tasks each of us will complete. | Basic gameplan laid out
Feb 9th | We will use a stack of tokens to manipulate the expressions | Token struct laid out; Makefile | Trying to break up expression into tokens | malloc not creating token array correctly | CLion, cmake, clang
Feb 10th |  | Correctly creates the token array Reads file input | Extensive testing done with creating token array | Slight bug with token splitting | CLion, cmake, clang
Feb 13th | Pair Programming | Token Stack complete; Compiles on all | Pushed everything and popped everything | Difference between compilers | Clion, cmake, clang
Feb 13th |  |  |  | Parentheses Not handled correctly | Clion, cmake, clang, gcc
Feb 15th |  | Parentheses and Neg integers done | Testing with different inputs | Not correctly incrementing through string | Clion, cmake, clang, gcc
Feb 17th | Kira and Emily facing some bugs with post/pre fix notations | Fixed everything. | Gave sample inputs of different kinds | Not correctly handling negative numbers or multi-digit integers.
20170217 | dcstarne | Preassessment | gcc | Execute: ./main input.txt output.txt