## Sheet1
Date | Discussions | Progress | Testing Done | Bugs Found/Fixed | Tools
Feb. 8th | Discussed the different tasks each of us will complete. | Basic gameplan laid out
Feb 9th | We will use a stack of tokens to manipulate the expressions | Token struct laid out; Makefile | Trying to break up expression into tokens | malloc not creating token array correctly | CLion, cmake, clang
Feb 10th |  | Correctly creates the token array Reads file input | Extensive testing done with creating token array | Slight bug with token splitting | CLion, cmake, clang
Feb 13th | Pair Programming | Token Stack complete | Pushed everything and popped everything | Difference between compilers | Clion, cmake, clang